## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 | Milestone 1 | US-01 | Study defect analysis workflow, RAG architecture and semantic similarity techniques | Must | — | Project Team | Completed
Milestone 1 | Milestone 1 | US-02 | Design system architecture and develop Bug Submission Module | Must | US-01 | Project Team | Completed
Milestone 1 | Milestone 1 | US-03 | Build historical defect knowledge base using chunking, embeddings and FAISS | Must | US-01 | Project Team | Completed
Milestone 2 | Milestone 2 | US-04 | Develop Triage Agent for severity, priority and component classification | Must | US-03 | Project Team | Completed
Milestone 2 | Milestone 2 | US-05 | Develop Log Analysis Agent for exception type, failure point and code path | Must | US-03 | Project Team | Completed
Milestone 2 | Milestone 2 | US-06 | Implement multi-agent orchestration and validate varied bug formats | Must | US-04, US-05 | Project Team | Completed
Milestone 3 | Milestone 3 | US-07 | Implement duplicate detection using semantic similarity and historical bugs | Must | US-03 | Project Team | Completed
Milestone 3 | Milestone 3 | US-08 | Implement root-cause analysis and remediation recommendations | Must | US-04, US-05, US-07 | Project Team | Completed
Milestone 3 | Milestone 3 | US-09 | Integrate Streamlit frontend with analysis and retrieval modules | Must | US-04–US-08 | Project Team | Completed
Milestone 4 | Milestone 4 | US-10 | Develop Defect Pattern Analytics Dashboard | Must | US-09 | Project Team | Completed
Milestone 4 | Milestone 4 | US-11 | Implement knowledge-base growth mechanism for verified resolved bugs | Must | US-03, US-07 | Project Team | Completed
Milestone 4 | Milestone 4 | US-12 | Conduct end-to-end testing and validate agent accuracy, duplicate detection quality and recommendation relevance | Must | US-04–US-11 | Project Team | Completed
Milestone 4 | Milestone 4 | US-13 | Prepare technical documentation, project report and final demonstration | Must | US-10–US-12 | Project Team | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate | Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US-01 | T01 | Study defect analysis workflow and defect lifecycle |  |  | Project Team | Research | Completed | 4 | 4 | Day 1: Done
US-01 | T02 | Study RAG architecture and semantic similarity techniques |  |  | Project Team | Research | Completed | 4 | 4 | Day 1: Done
US-02 | T03 | Design end-to-end architecture and Bug Submission Module |  |  | Project Team | Development | Completed | 6 | 6 | Day 1: Done
US-03 | T04 | Preprocess historical Bugzilla reports and create chunks |  |  | Project Team | Knowledge Base | Completed | 6 | 6 | Day 1: Done
US-03 | T05 | Generate Sentence Transformer embeddings and build FAISS index |  |  | Project Team | Knowledge Base | Completed | 6 | 6 | Day 1: Done
US-04 | T06 | Implement Triage Agent and component/severity/priority outputs |  |  | Project Team | Agent Development | Completed | 8 | 8 | Day 1: Done
US-05 | T07 | Implement Log Analysis Agent for exception and failure-point extraction |  |  | Project Team | Agent Development | Completed | 8 | 8 | Day 1: Done
US-06 | T08 | Integrate agent orchestration and save combined analysis history |  |  | Project Team | Integration | Completed | 8 | 8 | Day 1: Done
US-07 | T09 | Implement duplicate detection using similarity score and threshold |  |  | Project Team | Retrieval | Completed | 6 | 6 | Day 1: Done
US-08 | T10 | Implement root-cause analysis and remediation recommendation sections |  |  | Project Team | Agent Development | Completed | 8 | 8 | Day 1: Done
US-09 | T11 | Integrate Streamlit UI with analysis, similar bugs and recommendations |  |  | Project Team | Frontend/Integration | Completed | 8 | 8 | Day 1: Done
US-10 | T12 | Develop Defect Pattern Analytics for severity, priority and components |  |  | Project Team | Analytics | Completed | 6 | 6 | Day 1: Done
US-11 | T13 | Implement verified resolved-bug addition to knowledge base and FAISS |  |  | Project Team | Knowledge Base Growth | Completed | 6 | 6 | Day 1: Done
US-12 | T14 | Validate agent accuracy on five test cases |  |  | Project Team | Testing | Completed | 5 | 5 | Day 1: Done
US-12 | T15 | Evaluate duplicate detection quality on five test cases |  |  | Project Team | Testing | Completed | 4 | 4 | Day 1: Done
US-12 | T16 | Evaluate recommendation relevance and historical dataset sizes |  |  | Project Team | Testing | Completed | 5 | 5 | Day 1: Done
US-13 | T17 | Prepare technical documentation and project report content |  |  | Project Team | Documentation | Completed | 8 | 8 | Day 1: Done
US-13 | T18 | Prepare final demonstration with five distinct bug submissions |  |  | Project Team | Demonstration | Completed | 6 | 6 | Day 1: Done

## Stand up Meeting
Sprint | Day / Work Period | Impediments | Action Taken
Milestone 1 | Knowledge-base and architecture work | Large historical dataset and vector-index preparation required careful preprocessing | Built preprocessing, chunking, embedding and FAISS workflow
Milestone 2 | Agent development and integration | Agents needed validation across different bug formats | Implemented Triage, Log Analysis and orchestration with evaluation cases
Milestone 3 | Retrieval, duplicate detection and remediation | Duplicate quality and recommendation outputs needed measurable validation | Added evaluation scripts and integrated historical retrieval with remediation
Milestone 4 | Analytics, knowledge-base growth and end-to-end validation | Embedding/index consistency and UI retrieval mapping required verification | Rebuilt embeddings/index when needed, validated 268/268 consistency, fixed invalid-index handling, prepared evidence

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Milestone 1 |  |  | Project Team | Use structured defect chunks and a reproducible retrieval pipeline | Avoid inconsistent dataset/index states | Continue modular preprocessing and retrieval design | Created the historical knowledge base with chunks, embeddings and FAISS
2 | Milestone 2 |  |  | Project Team | Validate each agent with representative cases | Avoid relying on unvalidated outputs | Continue modular agent responsibilities | Created five-case accuracy evaluation
3 | Milestone 3 |  |  | Project Team | Use historical similarity to support duplicate detection and recommendations | Avoid treating similarity alone as complete root-cause proof | Continue evidence-based remediation | Evaluated duplicate detection and recommendation relevance
4 | Milestone 4 |  |  | Project Team | Measure quality with explicit metrics and dataset-size checks | Avoid unnecessary extra project files | Continue documenting test evidence and demo flow | Completed agent accuracy, duplicate quality, recommendation relevance and dataset consistency checks

## Project Summary & Evidence
Item | Recorded Work / Evidence
Project | AI Smart Bug Analyzer & Fix Advisor
Program | Infosys Springboard Internship
Purpose | Analyze software defects using a multi-agent pipeline, retrieve similar historical defects, identify root causes and provide remediation recommendations.
Pipeline | Bug Submission → Log Analysis → Triage → Root Cause Analysis → Duplicate Detection / Historical Retrieval → Remediation Recommendation → Defect Pattern Analytics / Knowledge Base Growth
Milestone 1 | Studied defect-analysis workflow, RAG architecture and semantic similarity; designed architecture; developed Bug Submission Module; built historical defect knowledge base.
Milestone 2 | Developed Triage Agent, Log Analysis Agent and multi-agent orchestration; validated agents on varied bug cases.
Milestone 3 | Implemented duplicate detection, root-cause analysis, remediation recommendations, Streamlit integration and combined analysis history.
Milestone 4 | Implemented Defect Pattern Analytics, verified resolved-bug knowledge-base growth, conducted end-to-end testing, and prepared documentation, project report and final demonstration.
Agent Accuracy | Triage: 3/5 = 60.00%; Log Analysis: 5/5 = 100.00%; Root Cause: 5/5 = 100.00%; Overall: 13/15 = 86.67%.
Duplicate Detection Quality | 5 cases evaluated; 4 correct and 1 incorrect = 80.00% for the evaluation set.
Recommendation Relevance | Recommended Fix: Relevant; Code-Level Suggestions: Relevant; Preventive Measures: Relevant. Result: 3/3 relevant sections.
Historical Dataset | 268 text chunks, 268 embeddings, 268 FAISS vectors; embedding/vector dimension 384.
Dataset Size Testing | Tested dataset sizes 50, 150 and 268. Top results: 5. Final checks: Embeddings/FAISS MATCH and Chunks/FAISS MATCH.
Defect Pattern Analytics | Dashboard includes severity distribution, priority distribution and frequently affected components; patterns are derived from analyzed defect history.
Knowledge Base Growth | Verified/resolved bugs can be added back to the historical knowledge base so future similarity retrieval can use the newly resolved example.
Key Files | app.py; preprocess.py; chunking.py; embedding.py; faiss_index.py; similarity_search.py; orchestrator.py; defect_pattern_analytics.py; evaluation scripts; analysis_history.json; chunks.txt; embeddings.npy; bug_index.faiss.
Milestone 1 Date Evidence | Milestone 1 work was recorded as 30 June – 9 July in the project plan.
Final Validation Status | Core Milestone 4 implementation and validation activities recorded here are based on the work evidence provided during the project.